## Version History
Project:ELINA ISMS&Web-portal
Author
Function | Name | Department Code
Project Manager | Elangovan | Technology Services
Version History
Date | Version | Summary of Changes
3rd April 2024 | 1.0 (Draft) | Initial Version by chitra
8th April 2024 | 1.0(Final) | Controlled Version
Approvals
Date | Validated by | Approved by
Updated and Validated on 5th April 2024 | Aathish
Rizwan
Updated and Validated on 8th April 2024 | Aathish
Note on B22: 08th April 2024:Aathish added-php configuration and settings: 1)Extension also enabled correctly 2)Temporary memory path is need to be correct

## System Requirements
Azure Checklist on ISMS and web-portal
S. No | Type | Description | Date of Completion
1 | Server team confirmation | Need to check the Server is up and running and get confirmed by the server team
Inform about the server movement to all the Stakeholders(ELINA + TTIPL)
2 | Application Configuration | Check Apache 2.4 status to ensure seamless operation Note: 1)Installation of Apache to be verified and visit the Apache site is working 2)Appropriate Listener Ports for the Project to be added on httpd.config file Port numbers: 1)80 for web portal 2)60161 for web 3)60162 for API 4)443 for HTTPS 3)Project public path with port number to be defined on the host files(vhost and SSL) 4)Need to increase the limitation of the number of user count from default settings
SSL configuration in Apache server ready with update wide card SSL Note: 1)Need to check SSL on Global SSL checker portal through online website
Verify PHP version 8.0.22 and Laravel version 8.83.27 compatibility with Drupal and Laravel.
Ensure compatibility of MySQL version 8 with requirements for the Web Portal and ISMS
Verify the Secure Sockets Layer (SSL) configuration on the Apache host to ensure that the application is running on SSL. Note: 1)visit the site(domain) with the secure https URL 2)Make sure to redirect from the HTTP to HTTPS 3)Ensure that redirection of domain from the elinaservices.in to elinaservices.com also its functionning properly.
3 | Confirmation from Elina Team | Need to Get an OTP from Elina Team for Godaddy
Notify the relevant personnel regarding the unavailability of the on-premises server, followed by the successful deployment and activation of the Azure server to ensure continuity of services.
Need to Get approval from the Elina Team after the System Integration Testing to ensure that system as working Perfectly

## Server Configuration
S. No | Type | Description | Date of Completion
1 | Remote Desktop protocol(RDP) | When needed only open the remote desktop Note: 1)It should be maintained the log as incident report sheet |  | To be maintained as a separate incident report sheet
2 | Operating System | Windows Server 2019 Datacenter
3 | File movement | file Movement should done from the cloud like Gdrive Note: 1)The kind of files are you moving as database exports
4 | Antivirus | virus and ransomware protection should enable and scan Note: 1)The antivirus named as Trendmicro 2)It can scan every week Saturday 3)It can done automatically
5 | Backup | periodical backup procedure should be followed like a database backup Note: 1)Period of Backup: i)weekly twice -database backup ii)Monthly once iii)Yearly once 2)It can be done manually by a backup administrator with the destination Google Cloud 3)Backup file should be done by Cloud 4)The retrieve option for the backup can only done by the administrator.
6 | Server security patchs updation | Need to check periodically the patch updates for the server Note: 1)It can be microsoft system patch 2)It can be done manually by an administrator because of the microsoft updation
7 | C-drive size | Memory should not exceed 50GB Note: 1) When exceeding the size we need to add an external drive to increase memory 2)Increasing the disk size to 256GB

## web-portal Checklist
Azure Checklist on Web-portal
S. No | Type | Description | Date of Completion
1 | Project Configuration | Determine whether to proceed with a domain name or an IP address for system configuration, ensuring compatibility and adherence to established protocols.
2 | Environment Configuration | Verify the validity and functionality of Google Captcha keys, ensuring they are correctly configured and operational for secure authentication purposes. Note: 1)need to check the site key and secret key
3 | Code & DB movement | Git Clone done on the premises server and also informed the downtime will be there in a premises server
Migrate the updated database seamlessly from the on-premises server environment to Azure, ensuring data integrity and consistency, facilitating smooth transition and uninterrupted operations. Note:clear cache and push latest code to git with the latest DB
Exporting the database of mysql_configuration to check the maxallowed_packet to check the current database size is maximum of maxallowed_packet if there are maximum restart mysql and import the database Note: 1)max_allowed_packet in my.ini (in mysql) should be greater than DB size
Adding all the isms redirection links and API-endpoints for the web-portal
Verify the operational status of the database and clear the cache, ensuring its availability and functionality for data storage and retrieval processes. Note: 1)Need to check the database connection "./vendor/bin/drush status" 2)Clearing the cache "./vendor/bin/drush cr"
4 | Testing | Conduct comprehensive smoke testing across all functionalities to validate system integrity and identify potential issues promptly, ensuring robustness and reliability prior to deployment. Note: 1)Checking every links and functionalities
after the testing completion should change from IP to domain name

## ISMS Checklist
Azure Checklist on ISMS
S. No | Type | Description | Date of Completion
1 | System Configuration | Validate the integrity and functionality of Internet Information Services (IIS) to ensure proper handling of API gateways. Note: 1)Check IIS Installation: Ensure that IIS is installed on the server where you intend to host the API gateway. You can verify this by checking the Windows features or using the Server Manager. 2)2)windows server hosting need to be installed. 3)Review Site Bindings: Check the site bindings to ensure that the API gateway site is properly configured to listen on the desired port. 4)Test Site Accessibility: Use a web browser or a command-line tool like curl to access the API gateway site using its URL.Confirm that the site loads without errors and responds with the expected content or status codes.
Validate the Composer setup to ensure compatibility with PHP version 8.0.22 and Laravel version 8.83.27 Note: 1)Adding the Config file in both web and API 2)Clearing the Cache
Need to install the Composer
Checking the PHP configuration and settings Note: 1)Memory Limit 2)Uploaded File Limit 3)Extension also enabled correctly 4)Temporary memory path is need to be correct
2 | Project Configuration | Ensure that verification, including database port numbers, to guarantee seamless connectivity Note: 1)The database port number 3306 matches the env port number 2)Need to check the database name,username and Password
Inspect the Base URL on the Config file within Setting.php for both web and API and gateway URL. Note: 1)Need to check google captcha key on the setting.php
3 | Third party tool | Verify the functionality and compatibility of Google APIs Note: 1)Checking the valid email address 2)Checking the authentication files are appropriate to the email address and email domain extensions(Eg:elinaservices.in)
Validate the SMTP configuration of Azure to ensure smooth email communication, covering aspects like server authentication, port settings, and security protocols, guaranteeing reliable transmission of messages and notifications within the system. Note: 1)SMTP configuration to be verified(Port,driver,credientils as email-id and password)
4 | Code & DB movement | Need to validate the version sync of the production Environment and UAT Environment and git repository.
Retrieve the latest code updates from the GitHub repository, ensuring compatibility and integrity, before seamlessly deploying them onto the Azure platform.
Migrate the updated database from the on-premises server environment to Azure.
Update the database content securely, ensuring data accuracy and integrity, while handling unknown characters appropriately to maintain data consistency and reliability during the transition process.
Export existing reports files stored on the on-premises servers and seamlessly import them into Azure,
Perform a thorough cache clearance for both web and API systems, followed by a seamless IIS restart, ensuring optimal performance and resolving any potential caching issues to maintain system efficiency and responsiveness.
5 | Testing | Conduct comprehensive smoke testing across all functionalities to validate system integrity and identify potential issues promptly, ensuring robustness and reliability prior to deployment.

## Drupal plugins
Azure Checklist plugins on Web-portal
S. No | Module List
1 | CKEditor 5
2 | Field Formatter Class
3 | Field Group
4 | Datetime
5 | CSS Editor
6 | Font Awesome
7 | Page Specific Class
8 | Social Media Links
9 | Paragraph
10 | RESTful Web Services
11 | HTTP Basic Authentication
12 | CAPTCHA

## GIT
SI.NO | Git Branch Name
1) | Master
2) | Aathish
3) | chitra_sail
4) | chitra_isms
5) | hotfix
6) | merge_control